## Plan
Plan ID | Plan name | Date of export
EwNxVBTFnUKGr6h7974-OskADxz7 | R26-IT-021 | 2026-10-14

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
8CKxfZYBo0eS4m0SVS091MkAEmTh | Review Herbal Knowledge component feedback from PP1 | Initiating |  | Completed | Important | IT22640598 MUNASINGHE M P | IT22640598 MUNASINGHE M P | 2026-08-30 | 2026-05-21 |  |  | false | 2026-10-13 | IT22640598 MUNASINGHE M P
CGnoimPIlEKKqTbIhepdt8kAE-Cx | Review PP1 panel feedback and identify required improvements | Initiating |  | Completed | Important | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-13 | 2026-05-22 | 2026-05-15 |  | false | 2026-10-13 | PATTIYA ARACHCHI P.A.H.K. it22112132
znnGZW7ppE2hPHB7v1xMXckAIiZ- | Re-evaluate the medicinal plant quality assessment methodology | Planning |  | Completed | Important | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-13 | 2026-05-30 | 2026-05-22 |  | false | 2026-10-13 | PATTIYA ARACHCHI P.A.H.K. it22112132
-qeHj6jcm0G5qb4U740mDckAFRNq | Finalize curated medicinal plant and knowledge scope | Planning |  | Completed | Medium | IT22640598 MUNASINGHE M P | IT22640598 MUNASINGHE M P | 2026-10-13 | 2026-05-31 | 2026-05-23 |  | false | 2026-10-13 | IT22640598 MUNASINGHE M P
mAfViw26QkiAU65P1OOSuskAIFxJ | Conduct additional literature review on plant disease detection and maturity classification | Planning |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-13 | 2026-06-06 | 2026-05-31 |  | false | 2026-10-13 | PATTIYA ARACHCHI P.A.H.K. it22112132
gK6SrnjfmECOl-ETBEFiuMkAM2cp | Clean bilingual herbal entries and prepare text chunks | Executing |  | Completed | Medium | IT22640598 MUNASINGHE M P | IT22640598 MUNASINGHE M P | 2026-10-13 | 2026-08-31 | 2026-06-07 |  | false | 2026-10-13 | IT22640598 MUNASINGHE M P
V8ZpsFrjyEyn8nb1cpKsIskAPfVh | Design the proposed three-stage deep learning prediction pipeline | No Bucket |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-13 | 2026-06-09 | 2026-06-07 |  | false | 2026-10-13 | PATTIYA ARACHCHI P.A.H.K. it22112132
AdjKfyCEakO4S54oepsuk8kAE4UK | Research common leaf diseases and their visible symptoms | Executing |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-14 | 2026-06-27 | 2026-06-10 |  | false | 2026-10-14 | PATTIYA ARACHCHI P.A.H.K. it22112132
zmVJxvl-2EuH9ZsKx-l4NMkAPnec | Configure multilingual embeddings and ChromaDB index | Executing |  | Completed | Medium | IT22640598 MUNASINGHE M P | IT22640598 MUNASINGHE M P | 2026-10-13 | 2026-08-31 | 2026-06-26 |  | false | 2026-10-13 | IT22640598 MUNASINGHE M P
4jTADZrUWE2QBl7hd0hUWMkAF_Xc | Create the species-specific disease knowledge CSV | Executing |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-14 | 2026-07-04 | 2026-07-01 |  | false | 2026-10-14 | PATTIYA ARACHCHI P.A.H.K. it22112132
NwdY2MyqyE2-BSr22wq-7ckAHwzB | Develop Model 2: Species-Specific Disease and Health Classification | Executing |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-14 | 2026-07-11 | 2026-07-05 |  | false | 2026-10-14 | PATTIYA ARACHCHI P.A.H.K. it22112132
YL8PK6Y2P0Ogi3AXEKsCBskAGQuS | Develop Model 3: Leaf Maturity Stage Classification | Executing |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-14 | 2026-07-18 | 2026-07-12 |  | false | 2026-10-14 | PATTIYA ARACHCHI P.A.H.K. it22112132
X5ysheNo2kmXPtyw83uxlckALgXU | Implement LangChain retrieval and response pipeline | Executing |  | Completed | Medium | IT22640598 MUNASINGHE M P | IT22640598 MUNASINGHE M P | 2026-10-13 | 2026-09-03 | 2026-07-17 |  | false | 2026-10-13 | IT22640598 MUNASINGHE M P
Rbt85p1tAEyAtsKUHrgzY8kAENbs | Connect all three models into the sequential prediction pipeline | Executing |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-14 | 2026-07-25 | 2026-07-19 |  | false | 2026-10-14 | PATTIYA ARACHCHI P.A.H.K. it22112132
Enw9NYMew0C7Vlw0nBEAOskAJEVP | Add source-supported response formatting and safety handling | Executing |  | In progress | Medium | IT22640598 MUNASINGHE M P | IT22640598 MUNASINGHE M P | 2026-10-13 |  | 2026-07-16 |  | false
nypC2HGQtkGq4JC2ExFTy8kAGlfm | Implement medicinal suitability assessment based on prediction results | Executing |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-14 | 2026-08-01 | 2026-07-26 |  | false | 2026-10-14 | PATTIYA ARACHCHI P.A.H.K. it22112132
C6PbM-59HkODEFK5ql2I58kACOXn | Integrate Grad-CAM visualization for explainable predictions | Executing |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-14 | 2026-08-08 | 2026-08-02 |  | false | 2026-10-14 | PATTIYA ARACHCHI P.A.H.K. it22112132
Qp_vmpGgUUi9E98i3tBsrckAFHcb | Implement Flask chatbot endpoints | Executing |  | Completed | Medium | IT22640598 MUNASINGHE M P | IT22640598 MUNASINGHE M P | 2026-10-13 |  | 2026-08-07 |  | false | 2026-10-13 | IT22640598 MUNASINGHE M P
BLucW3k8x0ufBboS7KbrmMkAHmKi | Test the complete three-stage prediction workflow | Monitoring and controlling |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-14 | 2026-08-10 | 2026-08-09 |  | false | 2026-10-14 | PATTIYA ARACHCHI P.A.H.K. it22112132
O-Os3YUIJE68Kqc4YmX-_MkAIY-I | Implement Flask chatbot endpoints | Executing |  | Completed | Medium | IT22640598 MUNASINGHE M P | IT22640598 MUNASINGHE M P | 2026-10-13 |  | 2026-08-16 |  | false | 2026-10-13 | IT22640598 MUNASINGHE M P
L7ybGe-E2E2veAcNfCxpeskAHOjh | Test Sinhala and English retrieval and answer relevance | Monitoring and controlling |  | In progress | Medium | IT22640598 MUNASINGHE M P | IT22640598 MUNASINGHE M P | 2026-10-13 |  | 2026-07-31 |  | false
JLEjzVMBAUaKp8--ztFGackAEEk_ | Prepare Progress 2 slides and working component demos | Monitoring and controlling |  | Completed | Medium | IT22640598 MUNASINGHE M P;WICKRAMASINGHE D G T K it22132796;H.D. SACHINTHA it22168986;PATTIYA ARACHCHI P.A.H.K. it22112132 | IT22640598 MUNASINGHE M P | 2026-10-13 | 2026-08-31 | 2026-08-22 |  | false | 2026-10-13 | IT22640598 MUNASINGHE M P
t8vx-vhRnEeKg20N8B-MBMkAPgFQ | Capture and assign Progress 2 panel feedback | Monitoring and controlling |  | Completed | Medium | IT22640598 MUNASINGHE M P;WICKRAMASINGHE D G T K it22132796;H.D. SACHINTHA it22168986;PATTIYA ARACHCHI P.A.H.K. it22112132 | IT22640598 MUNASINGHE M P | 2026-10-13 |  | 2026-09-03 |  | false | 2026-10-14 | IT22640598 MUNASINGHE M P
qJSn9Nkg6UyRkHZg1cZ53MkABucX | Analyze limitations of single-image plant quality classification | Planning |  | Completed | Important | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-14 | 2026-09-12 | 2026-09-06 |  | false | 2026-10-14 | PATTIYA ARACHCHI P.A.H.K. it22112132
OkjKczWM50mmzSbxtrAa0ckAPLBF | Design multi-image assessment for more representative plant evaluation | Planning |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-14 | 2026-09-19 | 2026-09-13 |  | false | 2026-10-14 | PATTIYA ARACHCHI P.A.H.K. it22112132
ivCKVIP_R0Wwtmu_6zBTyMkABMzk | Implement multi-image assessment for more representative plant evaluation | Executing |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-14 | 2026-09-26 | 2026-09-20 |  | false | 2026-10-14 | PATTIYA ARACHCHI P.A.H.K. it22112132
OTK8kQcHeECFi61gg2yBLckAI7Nq | Test the Quality assessment component work flow | Monitoring and controlling |  | Completed | Medium | PATTIYA ARACHCHI P.A.H.K. it22112132 | PATTIYA ARACHCHI P.A.H.K. it22112132 | 2026-10-14 | 2026-09-28 | 2026-09-27 |  | false | 2026-10-14 | PATTIYA ARACHCHI P.A.H.K. it22112132
Gwf_RD1TPEep0A62LqmjDskAJggT | Complete individual draft theses | Closing |  | Completed | Important | IT22640598 MUNASINGHE M P;WICKRAMASINGHE D G T K it22132796;H.D. SACHINTHA it22168986;PATTIYA ARACHCHI P.A.H.K. it22112132 | IT22640598 MUNASINGHE M P | 2026-10-13 |  | 2026-10-08 |  | false | 2026-10-13 | IT22640598 MUNASINGHE M P
euXOdrAj5U6gX_ePi8jouskAM8Md | Submit draft thesis | Closing |  | Completed | Important | IT22640598 MUNASINGHE M P;WICKRAMASINGHE D G T K it22132796;H.D. SACHINTHA it22168986;PATTIYA ARACHCHI P.A.H.K. it22112132 | IT22640598 MUNASINGHE M P | 2026-10-13 |  | 2026-10-11 |  | false | 2026-10-13 | IT22640598 MUNASINGHE M P
QAMAyLfdXkqPvV5aJQex6ckAANkE | Review research requirements and identify cultivation recommendation features | Planning |  | Completed | Important | WICKRAMASINGHE D G T K it22132796 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-05-21 | 2026-05-17 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
cEN5z-xZZ0KfrHUhSr5o9MkAM4LP | Collect medicinal plant cultivation data and reference information | Executing |  | Completed | Medium | WICKRAMASINGHE D G T K it22132796 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-06-10 | 2026-05-22 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
3jUJFNl6Mk-Z62BgaPYQGckAECmQ | Prepare and preprocess the medicinal plant cultivation dataset | Executing |  | Completed | Medium | WICKRAMASINGHE D G T K it22132796 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-06-25 | 2026-06-11 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
B4rBar5j5UumTSPYmRX3OckADDNc | Design the machine learning cultivation recommendation workflow | Planning |  | Completed | Medium | WICKRAMASINGHE D G T K it22132796 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-07-10 | 2026-06-26 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
Szb54lMbsUCFIeGnASpZMMkANwcr | Develop the Flask backend for cultivation recommendations | Executing |  | Completed | Medium | WICKRAMASINGHE D G T K it22132796 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-07-25 | 2026-07-11 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
OjymsOUSBUGKd8WfOYejmMkAK3G_ | Develop the Flutter cultivation recommendation interface | Executing |  | Completed | Medium | WICKRAMASINGHE D G T K it22132796 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-08-15 | 2026-07-26 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
ITzBcoNRY0Si8ty8J-GivskADjTv | Integrate the ML model with the backend and Flutter application | Executing |  | Completed | Medium | WICKRAMASINGHE D G T K it22132796 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-08-31 | 2026-08-16 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
GFmAS_7Jq0CPyqhuYjT37MkABHSM | Test the recommendation system and evaluate model performance | Monitoring and controlling |  | Completed | Medium | WICKRAMASINGHE D G T K it22132796 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-09-15 | 2026-09-01 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
JuXs7bauKkSnKTIOoTDs4skAHKtK | Review Progress Viva feedback and improve the ML dataset and model implementation | Monitoring and controlling |  | In progress | Medium | WICKRAMASINGHE D G T K it22132796 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-10-16 | 2026-10-12 |  | false
J1J5ZkoXxEqRTHfvXgxJG8kANU_i | Update individual thesis documentation and refine model evaluation results | Executing |  | In progress | Medium | WICKRAMASINGHE D G T K it22132796 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 |  | 2026-09-30 |  | false
-ErEgYr-40uukkp1smWsvskAOFXk | Review Progress Viva feedback and improve the ML dataset and model implementation | Monitoring and controlling |  | In progress | Medium | WICKRAMASINGHE D G T K it22132796 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 |  | 2026-09-03 |  | false
XtHtOOkaYkuAsa96UW8xiMkAMuFU | Review PP1 panel feedback and Identify the individual research component scope and objectives | Initiating |  | Completed | Important | WICKRAMASINGHE D G T K it22132796 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-05-22 |  |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
-eU5PgJP7UG_GIXwsiDO0MkAIpR2 | Review Research Requirements and Define Objectives | Initiating |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-05-21 |  |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
9ZMsCH52T0GDtF39vzlcGskAOnQ5 | Research Literature Review and Existing Plant Recognition Systems | Planning |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-05-28 | 2026-05-23 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
bpFhlNcVJ0O4x_3LW-79C8kAJv0Z | Collect Ayurvedic Plant Image Datasets | Executing |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-06-11 | 2026-05-29 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
JtvPOTv-qEWvLDBsDhplOskAD7Ju | Organize and Categorize Plant Images | Executing |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-06-18 | 2026-06-12 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
zUTsdZtFiU64Qv-gj0rCTskAJWDE | Review Image Quality and Perform Image Preprocessing | Executing |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-07-02 | 2026-06-19 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
AnhJzpfd30WQ3uwF6fkjw8kAFBcd | Study CNN Architectures and Select EfficientNet Model | Planning |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-07-16 | 2026-07-03 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
fOABm849qUCzK884Z4YGU8kALZcZ | Define Research Methodology and System Workflow | Planning |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-07-23 | 2026-07-17 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
zIlVjQ4Ru0Cqm3tUqxYQdMkADGG3 | Configure Model Training and Hyperparameters | Executing |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-08-06 | 2026-07-24 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
y04Ov3Z-9Eqn1iSDX9vpeskAMFlO | Train the Ayurvedic Plant Classification Model | Executing |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-08-20 | 2026-08-07 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
tofOaDDZ0UO3HHb5DJ1rmskAEiv1 | Design Flutter Mobile Application Architecture | Executing |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-08-26 | 2026-08-21 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
bmIa1CYRI0KEccxDICke0MkACBVQ | Research Additional Flower and Herbal Seed Datasets | Executing |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-09-02 | 2026-08-27 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
v1FGvjP1wkOkXfa-1vZoAMkAIwzj | Integrate Image Recognition Model with Mobile Application | Executing |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-09-10 | 2026-09-03 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
81_M9ZsXck2Lc4jerMBR4skANCku | Evaluate Model Accuracy and Generate Confusion Matrix | Monitoring and controlling |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-09-17 | 2026-09-11 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
dq5lxth1NkaSCxT2qqiBEMkAGRso | Test Plant Recognition Using Unseen Images | Monitoring and controlling |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-10-24 | 2026-09-18 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
veqpD0ALFUKbvjtX3dslZckAJ1b3 | Review Research Progress and Identify Improvements | Monitoring and controlling |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-09-30 | 2026-09-25 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
WSZL6PaPT0GESWSJckkjwskAEnVS | Improve Model Performance and Finalize System | Executing |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-10-04 | 2026-10-01 |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796
FzKrjEl46E2dqRssZnlV1ckALc2O | Submit Individual Thesis | Closing |  | Completed | Medium | H.D. SACHINTHA it22168986 | WICKRAMASINGHE D G T K it22132796 | 2026-10-14 | 2026-10-11 |  |  | false | 2026-10-14 | WICKRAMASINGHE D G T K it22132796

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
8CKxfZYBo0eS4m0SVS091MkAEmTh | Review Herbal Knowledge component feedback from PP1 | 8r-JwqWlGEGAG1erk06Ba8kABOiH |  | Completed | Important | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-08-30 | 2026-05-21 |  |  | false | 2026-10-13 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4
CGnoimPIlEKKqTbIhepdt8kAE-Cx | Review PP1 panel feedback and identify required improvements | 8r-JwqWlGEGAG1erk06Ba8kABOiH |  | Completed | Important | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-13 | 2026-05-22 | 2026-05-15 |  | false | 2026-10-13 | 51c339e9-318b-4eef-af46-9c043a177d76
znnGZW7ppE2hPHB7v1xMXckAIiZ- | Re-evaluate the medicinal plant quality assessment methodology | dYYXVIEFUkKNhffs8VXItckAGZwP |  | Completed | Important | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-13 | 2026-05-30 | 2026-05-22 |  | false | 2026-10-13 | 51c339e9-318b-4eef-af46-9c043a177d76
-qeHj6jcm0G5qb4U740mDckAFRNq | Finalize curated medicinal plant and knowledge scope | dYYXVIEFUkKNhffs8VXItckAGZwP |  | Completed | Medium | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-10-13 | 2026-05-31 | 2026-05-23 |  | false | 2026-10-13 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4
mAfViw26QkiAU65P1OOSuskAIFxJ | Conduct additional literature review on plant disease detection and maturity classification | dYYXVIEFUkKNhffs8VXItckAGZwP |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-13 | 2026-06-06 | 2026-05-31 |  | false | 2026-10-13 | 51c339e9-318b-4eef-af46-9c043a177d76
gK6SrnjfmECOl-ETBEFiuMkAM2cp | Clean bilingual herbal entries and prepare text chunks | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-10-13 | 2026-08-31 | 2026-06-07 |  | false | 2026-10-13 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4
V8ZpsFrjyEyn8nb1cpKsIskAPfVh | Design the proposed three-stage deep learning prediction pipeline |  |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-13 | 2026-06-09 | 2026-06-07 |  | false | 2026-10-13 | 51c339e9-318b-4eef-af46-9c043a177d76
AdjKfyCEakO4S54oepsuk8kAE4UK | Research common leaf diseases and their visible symptoms | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-14 | 2026-06-27 | 2026-06-10 |  | false | 2026-10-14 | 51c339e9-318b-4eef-af46-9c043a177d76
zmVJxvl-2EuH9ZsKx-l4NMkAPnec | Configure multilingual embeddings and ChromaDB index | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-10-13 | 2026-08-31 | 2026-06-26 |  | false | 2026-10-13 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4
4jTADZrUWE2QBl7hd0hUWMkAF_Xc | Create the species-specific disease knowledge CSV | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-14 | 2026-07-04 | 2026-07-01 |  | false | 2026-10-14 | 51c339e9-318b-4eef-af46-9c043a177d76
NwdY2MyqyE2-BSr22wq-7ckAHwzB | Develop Model 2: Species-Specific Disease and Health Classification | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-14 | 2026-07-11 | 2026-07-05 |  | false | 2026-10-14 | 51c339e9-318b-4eef-af46-9c043a177d76
YL8PK6Y2P0Ogi3AXEKsCBskAGQuS | Develop Model 3: Leaf Maturity Stage Classification | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-14 | 2026-07-18 | 2026-07-12 |  | false | 2026-10-14 | 51c339e9-318b-4eef-af46-9c043a177d76
X5ysheNo2kmXPtyw83uxlckALgXU | Implement LangChain retrieval and response pipeline | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-10-13 | 2026-09-03 | 2026-07-17 |  | false | 2026-10-13 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4
Rbt85p1tAEyAtsKUHrgzY8kAENbs | Connect all three models into the sequential prediction pipeline | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-14 | 2026-07-25 | 2026-07-19 |  | false | 2026-10-14 | 51c339e9-318b-4eef-af46-9c043a177d76
Enw9NYMew0C7Vlw0nBEAOskAJEVP | Add source-supported response formatting and safety handling | jLyhhiRmAkCNrRx6r5GsBskALVba |  | In progress | Medium | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-10-13 |  | 2026-07-16 |  | false
nypC2HGQtkGq4JC2ExFTy8kAGlfm | Implement medicinal suitability assessment based on prediction results | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-14 | 2026-08-01 | 2026-07-26 |  | false | 2026-10-14 | 51c339e9-318b-4eef-af46-9c043a177d76
C6PbM-59HkODEFK5ql2I58kACOXn | Integrate Grad-CAM visualization for explainable predictions | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-14 | 2026-08-08 | 2026-08-02 |  | false | 2026-10-14 | 51c339e9-318b-4eef-af46-9c043a177d76
Qp_vmpGgUUi9E98i3tBsrckAFHcb | Implement Flask chatbot endpoints | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-10-13 |  | 2026-08-07 |  | false | 2026-10-13 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4
BLucW3k8x0ufBboS7KbrmMkAHmKi | Test the complete three-stage prediction workflow | 5hgZQYQzjU6FhNyU66qYnckAGelL |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-14 | 2026-08-10 | 2026-08-09 |  | false | 2026-10-14 | 51c339e9-318b-4eef-af46-9c043a177d76
O-Os3YUIJE68Kqc4YmX-_MkAIY-I | Implement Flask chatbot endpoints | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-10-13 |  | 2026-08-16 |  | false | 2026-10-13 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4
L7ybGe-E2E2veAcNfCxpeskAHOjh | Test Sinhala and English retrieval and answer relevance | 5hgZQYQzjU6FhNyU66qYnckAGelL |  | In progress | Medium | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-10-13 |  | 2026-07-31 |  | false
JLEjzVMBAUaKp8--ztFGackAEEk_ | Prepare Progress 2 slides and working component demos | 5hgZQYQzjU6FhNyU66qYnckAGelL |  | Completed | Medium | ef892adb-9c5f-4ef4-a580-cc3625b4aad4;8460d3e7-cabb-4487-91c2-0420f3a5758f;1470ec66-d446-45f0-b827-22ca07a6c7fd;51c339e9-318b-4eef-af46-9c043a177d76 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-10-13 | 2026-08-31 | 2026-08-22 |  | false | 2026-10-13 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4
t8vx-vhRnEeKg20N8B-MBMkAPgFQ | Capture and assign Progress 2 panel feedback | 5hgZQYQzjU6FhNyU66qYnckAGelL |  | Completed | Medium | ef892adb-9c5f-4ef4-a580-cc3625b4aad4;8460d3e7-cabb-4487-91c2-0420f3a5758f;1470ec66-d446-45f0-b827-22ca07a6c7fd;51c339e9-318b-4eef-af46-9c043a177d76 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-10-13 |  | 2026-09-03 |  | false | 2026-10-14 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4
qJSn9Nkg6UyRkHZg1cZ53MkABucX | Analyze limitations of single-image plant quality classification | dYYXVIEFUkKNhffs8VXItckAGZwP |  | Completed | Important | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-14 | 2026-09-12 | 2026-09-06 |  | false | 2026-10-14 | 51c339e9-318b-4eef-af46-9c043a177d76
OkjKczWM50mmzSbxtrAa0ckAPLBF | Design multi-image assessment for more representative plant evaluation | dYYXVIEFUkKNhffs8VXItckAGZwP |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-14 | 2026-09-19 | 2026-09-13 |  | false | 2026-10-14 | 51c339e9-318b-4eef-af46-9c043a177d76
ivCKVIP_R0Wwtmu_6zBTyMkABMzk | Implement multi-image assessment for more representative plant evaluation | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-14 | 2026-09-26 | 2026-09-20 |  | false | 2026-10-14 | 51c339e9-318b-4eef-af46-9c043a177d76
OTK8kQcHeECFi61gg2yBLckAI7Nq | Test the Quality assessment component work flow | 5hgZQYQzjU6FhNyU66qYnckAGelL |  | Completed | Medium | 51c339e9-318b-4eef-af46-9c043a177d76 | 51c339e9-318b-4eef-af46-9c043a177d76 | 2026-10-14 | 2026-09-28 | 2026-09-27 |  | false | 2026-10-14 | 51c339e9-318b-4eef-af46-9c043a177d76
Gwf_RD1TPEep0A62LqmjDskAJggT | Complete individual draft theses | 8HXKyBonU0e9HVUC3VmN1ckAOSL6 |  | Completed | Important | ef892adb-9c5f-4ef4-a580-cc3625b4aad4;8460d3e7-cabb-4487-91c2-0420f3a5758f;1470ec66-d446-45f0-b827-22ca07a6c7fd;51c339e9-318b-4eef-af46-9c043a177d76 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-10-13 |  | 2026-10-08 |  | false | 2026-10-13 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4
euXOdrAj5U6gX_ePi8jouskAM8Md | Submit draft thesis | 8HXKyBonU0e9HVUC3VmN1ckAOSL6 |  | Completed | Important | ef892adb-9c5f-4ef4-a580-cc3625b4aad4;8460d3e7-cabb-4487-91c2-0420f3a5758f;1470ec66-d446-45f0-b827-22ca07a6c7fd;51c339e9-318b-4eef-af46-9c043a177d76 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | 2026-10-13 |  | 2026-10-11 |  | false | 2026-10-13 | ef892adb-9c5f-4ef4-a580-cc3625b4aad4
QAMAyLfdXkqPvV5aJQex6ckAANkE | Review research requirements and identify cultivation recommendation features | dYYXVIEFUkKNhffs8VXItckAGZwP |  | Completed | Important | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-05-21 | 2026-05-17 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
cEN5z-xZZ0KfrHUhSr5o9MkAM4LP | Collect medicinal plant cultivation data and reference information | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-06-10 | 2026-05-22 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
3jUJFNl6Mk-Z62BgaPYQGckAECmQ | Prepare and preprocess the medicinal plant cultivation dataset | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-06-25 | 2026-06-11 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
B4rBar5j5UumTSPYmRX3OckADDNc | Design the machine learning cultivation recommendation workflow | dYYXVIEFUkKNhffs8VXItckAGZwP |  | Completed | Medium | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-07-10 | 2026-06-26 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
Szb54lMbsUCFIeGnASpZMMkANwcr | Develop the Flask backend for cultivation recommendations | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-07-25 | 2026-07-11 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
OjymsOUSBUGKd8WfOYejmMkAK3G_ | Develop the Flutter cultivation recommendation interface | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-08-15 | 2026-07-26 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
ITzBcoNRY0Si8ty8J-GivskADjTv | Integrate the ML model with the backend and Flutter application | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-08-31 | 2026-08-16 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
GFmAS_7Jq0CPyqhuYjT37MkABHSM | Test the recommendation system and evaluate model performance | 5hgZQYQzjU6FhNyU66qYnckAGelL |  | Completed | Medium | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-09-15 | 2026-09-01 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
JuXs7bauKkSnKTIOoTDs4skAHKtK | Review Progress Viva feedback and improve the ML dataset and model implementation | 5hgZQYQzjU6FhNyU66qYnckAGelL |  | In progress | Medium | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-10-16 | 2026-10-12 |  | false
J1J5ZkoXxEqRTHfvXgxJG8kANU_i | Update individual thesis documentation and refine model evaluation results | jLyhhiRmAkCNrRx6r5GsBskALVba |  | In progress | Medium | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 |  | 2026-09-30 |  | false
-ErEgYr-40uukkp1smWsvskAOFXk | Review Progress Viva feedback and improve the ML dataset and model implementation | 5hgZQYQzjU6FhNyU66qYnckAGelL |  | In progress | Medium | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 |  | 2026-09-03 |  | false
XtHtOOkaYkuAsa96UW8xiMkAMuFU | Review PP1 panel feedback and Identify the individual research component scope and objectives | 8r-JwqWlGEGAG1erk06Ba8kABOiH |  | Completed | Important | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-05-22 |  |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
-eU5PgJP7UG_GIXwsiDO0MkAIpR2 | Review Research Requirements and Define Objectives | 8r-JwqWlGEGAG1erk06Ba8kABOiH |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-05-21 |  |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
9ZMsCH52T0GDtF39vzlcGskAOnQ5 | Research Literature Review and Existing Plant Recognition Systems | dYYXVIEFUkKNhffs8VXItckAGZwP |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-05-28 | 2026-05-23 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
bpFhlNcVJ0O4x_3LW-79C8kAJv0Z | Collect Ayurvedic Plant Image Datasets | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-06-11 | 2026-05-29 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
JtvPOTv-qEWvLDBsDhplOskAD7Ju | Organize and Categorize Plant Images | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-06-18 | 2026-06-12 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
zUTsdZtFiU64Qv-gj0rCTskAJWDE | Review Image Quality and Perform Image Preprocessing | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-07-02 | 2026-06-19 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
AnhJzpfd30WQ3uwF6fkjw8kAFBcd | Study CNN Architectures and Select EfficientNet Model | dYYXVIEFUkKNhffs8VXItckAGZwP |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-07-16 | 2026-07-03 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
fOABm849qUCzK884Z4YGU8kALZcZ | Define Research Methodology and System Workflow | dYYXVIEFUkKNhffs8VXItckAGZwP |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-07-23 | 2026-07-17 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
zIlVjQ4Ru0Cqm3tUqxYQdMkADGG3 | Configure Model Training and Hyperparameters | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-08-06 | 2026-07-24 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
y04Ov3Z-9Eqn1iSDX9vpeskAMFlO | Train the Ayurvedic Plant Classification Model | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-08-20 | 2026-08-07 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
tofOaDDZ0UO3HHb5DJ1rmskAEiv1 | Design Flutter Mobile Application Architecture | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-08-26 | 2026-08-21 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
bmIa1CYRI0KEccxDICke0MkACBVQ | Research Additional Flower and Herbal Seed Datasets | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-09-02 | 2026-08-27 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
v1FGvjP1wkOkXfa-1vZoAMkAIwzj | Integrate Image Recognition Model with Mobile Application | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-09-10 | 2026-09-03 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
81_M9ZsXck2Lc4jerMBR4skANCku | Evaluate Model Accuracy and Generate Confusion Matrix | 5hgZQYQzjU6FhNyU66qYnckAGelL |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-09-17 | 2026-09-11 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
dq5lxth1NkaSCxT2qqiBEMkAGRso | Test Plant Recognition Using Unseen Images | 5hgZQYQzjU6FhNyU66qYnckAGelL |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-10-24 | 2026-09-18 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
veqpD0ALFUKbvjtX3dslZckAJ1b3 | Review Research Progress and Identify Improvements | 5hgZQYQzjU6FhNyU66qYnckAGelL |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-09-30 | 2026-09-25 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
WSZL6PaPT0GESWSJckkjwskAEnVS | Improve Model Performance and Finalize System | jLyhhiRmAkCNrRx6r5GsBskALVba |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-10-04 | 2026-10-01 |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f
FzKrjEl46E2dqRssZnlV1ckALc2O | Submit Individual Thesis | 8HXKyBonU0e9HVUC3VmN1ckAOSL6 |  | Completed | Medium | 1470ec66-d446-45f0-b827-22ca07a6c7fd | 8460d3e7-cabb-4487-91c2-0420f3a5758f | 2026-10-14 | 2026-10-11 |  |  | false | 2026-10-14 | 8460d3e7-cabb-4487-91c2-0420f3a5758f

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
8r-JwqWlGEGAG1erk06Ba8kABOiH | Initiating
dYYXVIEFUkKNhffs8VXItckAGZwP | Planning
jLyhhiRmAkCNrRx6r5GsBskALVba | Executing
5hgZQYQzjU6FhNyU66qYnckAGelL | Monitoring and controlling
8HXKyBonU0e9HVUC3VmN1ckAOSL6 | Closing

## Users
User ID | User Name | Email
ef892adb-9c5f-4ef4-a580-cc3625b4aad4 | IT22640598 MUNASINGHE M P | it22640598@my.sliit.lk
51c339e9-318b-4eef-af46-9c043a177d76 | PATTIYA ARACHCHI P.A.H.K. it22112132 | it22112132@my.sliit.lk
8460d3e7-cabb-4487-91c2-0420f3a5758f | WICKRAMASINGHE D G T K it22132796 | it22132796@my.sliit.lk
1470ec66-d446-45f0-b827-22ca07a6c7fd | H.D. SACHINTHA it22168986 | it22168986@my.sliit.lk